### Provincial, Territorial and National

Active School Community

Action Plans

2001-04

DRAFT No. 1

October 20, 2001

Provincial Action Plan:		2001-4

Newfoundland and Labrador

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Provincial delegates from this Roundtable to reconvene to discuss the outcomes |  |  |  |  |
| Link with Strategic Social Plan (1997) 6 regional committees Premier’s Advisory Committee Secretariat |  |  |  |  |
| Provincial Health Forum Submit questionnaire Attend forums (regional and provincial) |  | Nov 2001 |  |  |
| Do inventory of best practices (provincially and Federally/ Nationally) |  |  |  |  |
| Convene meeting of identified Ministries (with Deputy Ministers) to determine communications strategy |  |  |  |  |

Provincial Action Plan!		2001-4

Newfoundland and Labrador (page 2)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Identify pilot – school on physical activity program as part of Canadian Principal’s Association |  |  |  |  |
| Engage schools in provincial and national initiatives eg, walk to school, QDPE |  |  |  |  |
| Meet with school trustees principals, NTA to address and support quality physical activity programs |  |  |  |  |
| Prepare an annual calendar of events on physical activity for wide distribution |  |  |  |  |

Provincial Action Plan:		2001-4

Prince Edward Island

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Convene a meeting with health, education and recreation to determine immediate action for 2002 budget. |  |  |  |  |
| Provincial Roundtable |  |  | PEI ALA |  |
| Look at sustainability of current pilot projects (determine specific measurable outcomes) ie, Comprehensive school health, Rec 2000 |  |  |  |  |
| Active Healthy Schools Policy |  |  |  |  |
| Put together presentation for local Home and School Associations |  |  |  |  |
| Presentation to School Boards |  |  |  |  |
| Communication to general public concerning Alliance |  |  |  |  |

Provincial Action Plan:		2001-4

Prince Edward Island (page 2)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Arrange for central government support for Alliance (evaluation, social marketing, space, printing, etc) |  |  |  |  |
| Examine joint-use agreements for schools – work to erode barriers. Determine issues related to school access and priority scheme for use. |  |  | PEI RFA School Board |  |
| Examine current phys. Ed. Regulations |  | March 2002 | Phy. Ed Status Committee |  |

Provincial Action Plan:		2001-4

Nova Scotia

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Inventory of assets and existing coalitions in province. | Avoid duplication Share roles and responsibilities Identify gaps | 1 | Sport & Rec. Commission | Time |
| 2. Create a mechanism to lead and coordinate. | Provincial strategy Integrate into existing strategy | 1 | Coalition of Sport/Rec; Health, Education; Sport |  |
| 3. Develop a tool to help Active School Communities increate activity levels | Increase awareness and activity levels Pilot projects use tool | 1,2,3 | Education and Sport & Rec | Capacity (Staff $) |
| 4. Round Table messaging… relay these proceedings | Create awareness and motivation to action | 1 | Education, Health, Sport and Red | National Statement for consistency |
| 5. What does “Active School community” mean and what is expected of me? | Clarify roles, responsibilities and expectations Who should be/can be involved | 1,2 | Health; Sport & Rec; Education | Capacity (Staff, $) |
| 6. Meeting with Ministers | Share action plan | 1 | Tony Martin, Deputy Head SRC |  |

Provincial Action Plan:		2001-4

New Brunswick

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Establish Provincial Steering Committee | Call meeting Inventory Hold intersectoral forum | Dec 2001 Spring 2002 Winter 2003 | Heart/Stroke Stakeholders Partners |  |
| Letter to Minister of Health re: briefing and support | Meeting with minister Linkages with Health leaders Dialogue with other ministers Support for Provincial Steering Committee | Dec 2001 Jan 2002 Dec 2001 | Heart/Stroke |  |
| In-Service Training for Elementary Generalists | Trained generalists | Ongoing | Dept of Education |  |
| Active School Recognition Program | Recognize active schools through Minister’s Award | Spring 2002 | Dept of Education and Culture & Sport Secretariat |  |

Provincial Action Plan:		2001-4

Ontario

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1. Presentation to Ministers, ADM’s, DM’s | Creation of a tri-ministerial planning coordinating committee (Education, Health, Tourism Culture and Recreation) | Year 1 | OPHEA (heart & Stroke, OPHA, PRO, etc) | Presenters and material relevant to Active Schools Roundtable |
| 2. Develop policy position papers on areas that are key issues in promoting physical activity/ active school communities | Solutions/suggestions / strategies to focus on Shared use of resources Incentives QDPE/Phys. Ed Intersectoral collaboration Evaluation of guidelines Solutions to implementation barriers | Year 1, 2 | Parks and Rec Ontario (other partners) Active Living Networks | Input/support from different partner groups |
| 3. Continue to host Youth Summit (Active Schools Symposium) | Coordinated action plan – focus on advocacy | Year 2 | OPHEA | Money to bring people/resources together |
| 4. “Sustain a Coordinating Hub/Resource Centre” | Effective coordination, communication between stakeholders | Year 1,2 | OPHEA, Money sustained by Ministry of Health | $ funding |

Provincial Action Plan:		2001-4

Manitoba

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1. Coordinate with Alliance for Prevention of Chronic Disease in developing the Manitoba Physical Activity Strategy related to Active School Communities. Find results of Summit | Coordinated approach to addressing issue Provide basis of ongoing initiative |  |  |  |
| 2a) Heart and Stroke, take lead in calling a meeting of stakeholders b) identify leader(s) for Active School Communities | Get re-commitment from stakeholders | Immediately | Heart & Stroke, see that we all get report on Summit |  |
| 3. Go back to own groups to put this on agendas. Provincial groups coordinate with their national organizations (eg, CAHPERD, QDPE through MPETA) | Develop and deliver consistent messages | Ongoing | Each group |  |
| 4. Manitoba will ask key Min. to include this issue on next national agenda | Support national coordinated, consistent message | ASAP | Department staff |  |

Provincial Action Plan:		2001-4

Manitoba (page 2)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Put this on agenda (of conferences) for Pop Health Institute, Rec-Connections, Rec Volunteers’ Conference, SAG |  |  |  |  |
| Educate Parent Advisory Council about this issue and encourage them to address it at the school community level | Enlist parents as advocates for more physical activity with the Schools/communities | Ongoing |  |  |
| Incorporate Active School Communities into Summer Active and Winter Active campaigns |  | Immediate |  |  |
| Wish List: National voice to carry the issue |  |  |  |  |

Provincial Action Plan:		2001-4

Saskatchewan

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1. Provincial Roundtable | Mobilized and energized (Provincial strategy) | Year 1 (by Jan 31st) | SPRA Co-host with Provincial Government | Existing strategy paper circulated (A Physically Active” Saskatchewan) |
| 2. Identify needed Benchmarks | Identify existing data (needed) and fill in gaps | Year 1 (2-3 months) | Provincial Government |  |
| 3. Input to “Role of the School” document | Create network-intersectoral | ASAP | SPEA Minister contact Education | Enough copies of report |
| 4. Create public awareness | Have Provincial cabinet understand the inactivity “epidemic” Public must also understand epidemic | 4 months (Year 1) | Committee of Sask Action Strategy | Budget $ |
| Information Network established | Bring individual groups up to speed on what is being done | (3-4 months) | SPRA | Tobacco |
| Use “In Motion” (Saskatoon District Health Board) | See if this program could be applied provincially |  |  |  |

Provincial Action Plan!		2001-4

Alberta

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1. Joint letter from all attending associations will be sent to 3-4 Ministers (Learning, Health & Wellness, Community Develop Minister, Children’s Services) asking for a joint meeting to discuss the development of a forum to review Alberta status in this area. Present the health risks and update us on the Alberta Active Living Task Force | Meeting with 3 or 4 ministers | January meeting | ARPA |  |
| 2. Create an info package and distribute to identified stakeholders: Will have background of Roundtable Key messages Why the agency should get involved Give Roundtable strategies Include suggestions for action HPEC/CAHPERD | They will distribute the info to their networks | Dec/01 | Ever Active and Schools Come Alive |  |

Provincial Action Plan:		2001-4

British Columbia

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Sport and Physical Activity Branch (Ministry of Community Aboriginal and Women’s Services) has established working groups in the following areas: |  |  |  |  |
| 1. Active Country – com rec - workplace - home - preschool |  |  |  |  |
| 2. Active Schools - elementary - secondary - teacher education - support org. eg. Heart & Stroke |  |  |  |  |
| 3. Organized Sport - minor sport program - university sport - elite sport |  |  |  |  |
| - mandate to establish policy - look for collaboration opportunity - meeting of work groups in next month |  |  |  |  |

Provincial Action Plan:		2001-4

North  (Yukon, NWT, Nunavut)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1. Northern Forum |  |  |  |  |
| 2. Northern Media Campaign |  |  |  |  |
| 3. Northern Research |  |  |  |  |
| 4. Teacher Education Program - phys ed instruction review - curriculum tools and templates |  |  |  |  |
| Teacher Recruitment - coordinator messaging active school community theme | Changing teaching culture. |  |  |  |

Territorial Action Plan:		2001-4

Territory: Northwest Territories

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1. Update Phy. Ed Curriculum (QDPE philosophy) | Required Standards | By territory – NWT 12 mo |  |  |
| 2. Provide teachers with curriculum templates and tools to implement #1 | Practical means of applying the standards | 12 months |  |  |
| 3. Northern/Territorial roundtables | Buy-in across sectors |  |  |  |
| 4. Prepare a “Just the Facts” package for the north | Better mechanism to “sell” the idea | 6 months |  |  |
| 5. Develop a P.E. module for teacher education programs/ principal education programs | Affect future leaders “Influence the Future” | 2-3 years |  |  |
| 6. ECE/H&D/MALT coordination | Cross sectoral collaboration | By territory immediate |  |  |

Territorial Action Plan:		2001-4

Yukon

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1- research – Regionally (north) 1- APTN – Northern television – develop coordinated spots across the north – recognize language issue 1- meet with every school community |  |  |  |  |
| Lobby 3 ministers to approve a presentation to Commons | They agree | 1 month |  |  |
| Brief caucus | Other support | 1 month |  |  |
| Brief team on outcome of this roundtable to allow full consideration of a “Wellness unit” that could be formed to de-compartmentalize the silos | Full consideration | 1 month |  |  |
| Plan regular meetings (ever 2 months) to report progress to date on Action being taken by each group and to continue planning and implementation | Realize that further detailed plans need to be put together involving stakeholders Including kids! | 1-3 years |  |  |

Territorial Action Plan:		2001-4

Yukon (page 2)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Update phys ed plan |  |  |  |  |
| Provide teachers with templates and tools | Change criteria of the schools |  |  |  |
| Northern roundtables |  |  |  |  |
| Just the facts document for North |  |  |  |  |
| Phys ed module for teacher education training programs |  |  |  |  |
| Baseline data set, research, evidence-based decision making |  |  |  |  |
| Media awareness campaign |  |  |  |  |
| Getting foot in door |  |  |  |  |
| Meet with school councils to put on agenda at schools |  |  |  |  |
| Funding program for low income families |  |  |  |  |

Territorial Action Plan		2001-4

Yukon (page 3)  CIA) Collaboration/Information/Action

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Caucus briefing | Ministerial support across health/education/sport/justice | Fall 2001 | Carol, Bob, Pat |  |
| Presentation of “Renewal” | Creation of “Wellness Secretariat” | Fall 2001 | Bob |  |
| Awareness Presentations YMA School Councils District Area meetings YTA (Yukon Teachers Assoc) Health/Social Services Council Yukon Association of Municipalities |  |  |  |  |
| Creation of a presentation delivery kit |  |  |  |  |
| Active School Communities Coordinator | Provide support at the school level, coordinate and drive related issues |  |  |  |

Territorial Action Plan:		2001-4

Nunavut

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Nunavut scale conf. To pull together partners – eventual lead to Northern Roundtable | Set groundwork Set direction through consultation Bathurst Mandate |  | Dept CGT in conjunction with inter-departmental groups, ie, wellness. |  |
| Community Task Force established: DEA/Schools/Rec Coordinator Youth/Elders Wellness/Hamlet | Ownership at Community level |  |  |  |
| Public Awareness Campaign | Northbeat/APTN Relevancy up front |  |  |  |
| Schools/Hamlets – convention Recruitment of teachers Admin on side New way of Doing Business Rec Coordinator | Attend regional meetings On side thinking and buying into program |  |  |  |
| * Extraction of data – inclusion in data collection |  |  |  |  |

Territorial Action Plan:		2001-4

Nunavut (page 2)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| 1. Groundwork – intro. Building Healthy Communities | - Awareness, need - ownership, identify - willingness to promote | Now – Feb 02 | CGT and task force |  |
| 2. A.L. Strategy? P.A. Strategy? Volunteer Strategy? | Direction |  |  |  |
| 3. Community task force - DEA/School - Youth/elders - wellness/hamlet |  |  |  |  |
| PE curriculum update Provide curriculum resources Northern Roundtables Just the Facts – North NTEP contact Research Policy Public Awareness Campaign Communications |  |  |  |  |

National Action Plan:		2001-4

National

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| National Council on “ASC” – Active School Communities | Establish advocacy capacity Establish advocacy strategy Develop action plan and timelines for implementation of ASC concept Transform public and political perceptions regarding ASC Monitor develops of ASC concept Assist ministers/governments to raise (on the public agenda) the critical epidemic of physical inactivity among children and youth. Tool: Children and Youth Physical Activity Guide | 6/12 12-18/12 12/18/12 TBD TBD | TBD at this meeting Example: CIRA/ CAHPERD CPRA and health community Lead role to “site” this council | $ federal govt $ partners |

National Action Plan: 		2001-4

National Level (page 2)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| A cross-sectoral mechanism be established at the Pan-Canada level to ensure that he outcomes from this roundtable be advanced | Coordinated flow of information, action and communication | Year 1 At 30 months | Steering Committee | Capacity – meeting $ and support |
| Integrates all data related to inactivity | Articulate a clear and powerful picture of the problems related to inactivity (strong, capture the imagination of decision makers | Year 1 6 months | Cross-Sectoral mechanisms (Health, Sport, Community) | Capacity – money |
| Conduct a cost/benefit analysis of options for government and organizations | Well prepared arguments and specifications for all to take | Year 2 | Cross-Sectoral mechanisms (Health, Sport, Community) | Money |
| Develop key message(s) based on 2 and 3 and develop lobbying strategy | Lobbying campaign – removal of barriers | Year 2 | Cross-Sectoral mechanisms (Health, Sport, Community) | Money |

National Action Plan:		2001-4

National Level (page 3)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| Develop a national initiative and strengthen existing initiatives that ensure all children/youth have a safe and active place | Increased physical activity for children and youth | Year 3 | C-S Mech and CAP |  |
| That the outcomes of this roundtable are integrated into the development of the new legislation related to physical activity and sport and that policies be developed to address physical activity and active living | FIP/T Conference – Education Sport, Health Clear signal of the importance – entrench | Year 1 | Cross Sector and Sport Canada | Ongoing support |
| That the outcomes of this roundtable are integrated into the National Children’s Agenda | Better collaboration and integration |  |  |  |
| Development of a coordinated public awareness campaign | Increase physical activity Decrease negative affects of inactivity – obesity | Years 1-3 |  |  |
| Have a follow up forum to further engage ministers/councils and to assess our progress |  |  |  |  |

National Action Plan:		2001-4

National (page 4)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| National mechanism for coordinating advocacy (issues management) |  |  |  |  |
| Request briefing with Rock, Coderre, Justice, HROC, SEC State of Children and Youth, including Minister Furlong |  |  |  |  |
| Briefing with Landon Pearson |  |  |  |  |
| Share outcomes of orgs/networks not represented (B&G Club, National Child Care Federation) |  |  |  |  |
| Communicate outcomes through all internal networks (of this meeting) |  |  |  |  |
| Policy presentation Tool/ package - Kit - PPT - Web contents |  |  |  |  |

National Action Plan:		2001-4

National (page 5)

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |
| As national organizations we need to support the strategies requested by our provincial partners here today |  |  |  |  |
| “Power of One” presentation – commit to present issue |  | 1 month |  |  |
| Consolidate/disseminate research |  |  |  |  |
| Use children/youth guide as tool |  |  |  |  |
| Meet NSO’s to identify programs, initiatives and create compendium, list for use by all (shopping cart, MTI, Walk to School, QDPE) |  |  |  |  |

Provincial Action Plan:		2001-4

| Action | Desired Outcome | Timeline | Lead Responsibility | Resources Needed |
| --- | --- | --- | --- | --- |